## Instructions
Document Purpose and Instructions
[The purpose of this document is to capture and categorize all project requirements to ensure that they have been accurately described and can be tracked throughout the life of the projects. As requirements are added or deleted from the scope of work, this document should be updated and redistributed for approval, maintaining an accurate version history.
The table (see Matrix Grid tab) identifies fields for:
· “Unique Number” – Provide a unique identifier for each requirement to allow for tracing against project deliverables and testing activities. The naming convention can be as simple (1, 2, 3, etc.) or complex (e.g. multiple unique codes to identify the requirement by project, business unit, functional purpose, date added, SME assigned, etc.) as needed for your specific project. Documents that have more complex identifiers with unique coding should also include a legend for document reviewers.
· “Description” – a brief description of the requirement sufficient for the reader and project team to understand its purpose and how it will impact the final functionality of the project/product.
· “Requirement Origin” – name of the individual, role, organization, document etc. from which the requirement was originated. This will ensure that all the appropriate parties have been notified and consulted if a requirement needs to be better understood, revised and/or eliminated during the course of the project.
· “Business Priority” – examples of categorization would be High, Medium and Low; or Critical, Must Have and Nice to Have; Mandatory, Standard, Custom, Unnecessary. A legend must be provided to assist the reader and maintain consistency throughout the project.
· “Technical Priority” – examples of categorization would be High, Medium and Low; or Critical, Must Have and Nice to Have; or Complex, Moderate and Simple. A legend must be provided to assist the reader and maintain consistency throughout the project.
· “Estimate (cost, time)” – Initial requirements identified could be designated as In Scope to show that they have been included in the original baselined activity schedule. As requirements are either added or deleted, it will become necessary to capture the cost and time associated with each in order to fully realize the impact on the project cost and schedule remaining.
· “Phase, Release, Iteration” – Initial requirements should be identified as “in scope” or “out of scope” for project scheduling and costing. If the implementation will contain multiple phases or releases, requirements can further broken down into the appropriate work phase or release. This field can also be used to capture requirements that are identified during the course of the project for future enhancements and/or upgrades. By capturing the information in one document that is reviewed and confirmed throughout the project, all stakeholders will remain informed as to final project/product functionality.
Other fields can be added as needed for your specific project.

## Matrix Grid
Unique Number | Description (i.e. feature or function) | Requirement Origin | Business Priority | Technical Priority | Estimate (cost, time) | Phase, release, iteration
1 | The Audio Interface is compatible with the USB Audio Class 2.0 standard | Software developer | C | C | In scope (originial) | P0 | LEGEND:
2 | The Audio Interface can reproduce sound data with qualities up to 24 bits / 96 KHz | Hardware designer | C | C | In scope (originial) | P0 | Business Priority: | C - Critical M - Must have N - Nice to have
3 | The current quality of the audio being played is indicated with an LED. | Hardware designer | M | M | In scope (originial) | P0 | Technical Priority: | C - Complex M - Moderate S - Simple
4 | The Audio interface is compatible with iOS, and Android | Software developer | C | C | In scope (originial) | P0 | Phase: | P0 - Planning P1 - Initial Design P2 - Prototype Testing
5 | The Audio interface is compatible with iPadOS, Windows, and MAC | Software developer | N | M | In scope (originial) | P0
6 | An elegant case must be provided to secure the internal electronics | Customer | M | S | In scope (originial) | P0
7 | The power input for the Audio device comes from a standard barrel connector power supply | Hardware designer | N | M | In scope (originial) | P0
8 | The Audio Interface allows the user to change the volume of the analog output | Customer | N | S | In scope (originial) | P0
9 | The output of the Audio interface follows a standard for easy connection with audio equipment | Customer | M | S | In scope (originial) | P0
Reviewer/Approver | Rvwr | Apprv | Signature | Date
Executive Sponsor
Project Manager
Business Lead
Technical Lead
Stakeholder
Stakeholder

## SAMPLE
Unique Number | Description (i.e. feature or function) | Rqmt. Origin | Business Priority | Technical | Estimate (cost, time) | Phase, release, iteration
|  |  |  | Priority |  |  | LEGEND:
1 | Allow customers to place orders online | Customer Service Division | M | H | In Scope (original) | P1 | Business Priority: | M – Mandatory C - Custom S - Standard L - Low Level
2 | Allow customers to request items not in the catalog | Customer Service Division | C | L | In Scope (original) | R1 | Technical Priority: | H - High Need M - Moderate Need L - Low Need
3 | Add a wish list for customers to maintain future desired orders | Marketing | S | M | In Scope (original) | P1
4 | Build a chat function to answer customer questions online | Call Center Director | S | M | New Scope | P1
Reviewer/Approver | Rvwr | Apprv | Signature | Date
John Doe, Executive Sponsor |  | X
Jan Jones, Customer Service |  | X
Jeff Smith, Accounting | X